## Overview
FDE / PERSONAL LEARNING PLAN
Study planner
PLAN START 24 Oct 2026 ¦ 3.0 available hours / study day
DAILY AVAILABILITY |  |  |  | PLAN PROGRESS |  |  | REMAINING EFFORT |  | FORECAST FINISH
3 |  |  |  | 0% |  |  | 1080 |  | 09 Aug 2028
Total time before usability adjustment |  |  |  | Effort-weighted completion |  |  | Includes your contingency allowance |  | Selected scope and current allocations
READY ¦ 2.55 usable hours / study day across three shared-capacity tracks
01 Configure hours |  |  |  | 02 Update progress |  |  | 03 Log practice |  | 04 Review topics
Your daily capacity | [6 empty] | Next scheduled module by track
TRACK |  | SHARE |  | HOURS / DAY |  | REMAINING
Core |  | 60% |  | 1.53 |  | 693.6 | Core | FDE role and delivery orientation
Practice |  | 20% |  | 0.51 |  | 192 | Practice | DSA fundamentals and first pattern exercises
Delivery |  | 20% |  | 0.51 |  | 194.4 | Delivery | Discovery and business workflow framing
Hours chart excludes contingency. Daily allocations share one budget; idle capacity is not automatically reassigned.
NeetCode |  |  |  | LeetCode |  |  | Deep-ML |  | DataLemur
Planning estimates, not deadlines or a guarantee of mastery. Amber cells are editable. Protected cells prevent accidental formula changes; protection is not encryption. Start a new plan from the template.
Track | Daily usable hours |  | Track | Completed | Remaining
Core | 1.53 |  | Core | 0 | 578
Practice | 0.51 |  | Practice | 0 | 160
Delivery | 0.51 |  | Delivery | 0 | 162

## Read Me
Step / rule | Details | Overview
1. Enter your availability | Change the green inputs in Settings: start date, total hours per study day, study/rest pattern, contingency, usable fraction, and allocations.
2. Choose scope | Schedule contains 48 editable modules covering all 94 original FDE topics, explicit foundational bridges, practice, and capstone work. Optional alternatives start excluded. The 5,044 reference subtopics are not all mandatory.
3. Calibrate estimates | Hours are author-created planning assumptions, not measured course durations. Run a diagnostic, then edit estimates and progress. Keep essential prerequisites included; use 100% complete for demonstrated prior knowledge.
4. Read the forecast | Dashboard summarizes remaining effort, completion, and finish. Schedule has module dates. Weekly Timeline shows a fixed 104-week window; forecasts beyond it still have full dates.
5. Parallel does not mean extra capacity | Core, Practice, and Delivery share the same usable hours. Each lane is ordered sequentially; explicit prerequisites can delay another lane. Unused lane time is not automatically reallocated.
6. Capacity model | Remaining hours = estimate x (1-completion) x (1+contingency). Lane capacity = daily hours x usable fraction x lane share. Fractional study-day offsets preserve effort; calendar dates are rounded to study days.
7. Dependencies and blocks | Prerequisite IDs must exist earlier in Schedule and be included. Later references, missing IDs, disabled required tasks, invalid inputs, or zero capacity block the dependent work. Do not sort or reorder Schedule; use filters.
8. Completed work | Completion percentages describe demonstrated task evidence. Completed or skipped tasks have no remaining hours or forecast dates. Forecasts are for the remaining plan; they are not actual completion history.
9. Practice log | Record DSA, SQL, ML, or project practice and mistakes. Next review defaults to seven calendar days. Log entries do not automatically certify mastery or update Schedule percentages.
10. Holidays | Add up to 100 excluded dates in Holidays. Weekend pattern is seven text digits from Monday to Sunday; 0 means available and 1 means unavailable.
11. Module granularity | Topics are bundled into practical modules so related concepts and evidence can be learned together. Topic Map links each of the 94 topics to one module. Module estimates include its stated learning and exercise work; capstone modules are integrated implementation and review, not extra reading.
12. No false guarantees | Coverage and formula tests do not prove every concept is explained or every source correct. Domain knowledge, security/legal review, and real delivery experience remain role-dependent. This is a planning aid, not an employment guarantee.
13. No macros or connections | This XLSX uses formulas, validation, and formatting only. There are no macros, API calls, paid model calls, external data connections, or automatic account synchronization.
14. Preserve your edits | The build script overwrites this generated workbook only when explicitly requested. Rebuilding discards entered progress, estimates, holidays, and practice logs. Use the workbook itself for normal adjustments.
LeetCode DSA practice | https://leetcode.com/problemset/
NeetCode pattern roadmap | https://neetcode.io/roadmap
Deep-ML math and ML paths | https://www.deep-ml.com/paths
DataLemur SQL and DS practice | https://datalemur.com/
Coverage and practice guide | 08 Study Plan and Practice.md
Main roadmap | FDE Roadmap.md
PROFESSIONAL TEMPLATE GUIDE | This workbook preserves your source inputs and formulas. The separate XLTX starts a clean plan.
Editable cells | Amber fill and blue text identify inputs. Existing references to green cells in the original instructions now refer to these amber input cells.
Safe editing | Edit Settings B2:B9; Schedule D:J; Holidays A:B; and practice fields A:G and I. Module IDs, lanes, order, helper formulas, and topic mappings remain fixed.
Formula protection | Sheets are protected without a password against accidental edits. Review > Unprotect Sheet allows intentional customization. This is not a confidentiality or encryption control.
New plan | Open FDE Study Planner - Template.xltx to create a new workbook, change the start date and hours, select the scope, and save under a new name.
Preserved professional copy | Use FDE Study Planner - Professional.xlsx for the current plan. Do not rebuild it over your progress.
Calendar and chart scope | The weekly chart retains all 104 weeks. The overview PDF is a one-page snapshot; live charts and dates recalculate in Excel.
Printing | Landscape print areas, repeated headers, and page footers are set. The full weekly timeline spans four printed pages across to avoid unreadably small text.

## Settings
Setting | Editable Value | Meaning | Overview
Start date | 2026-10-24 | Dates are forecasts for remaining work, not records of actual completion.
Hours available per study day | 3 | One total daily budget shared by all lanes; change this first.
Weekend pattern Monday to Sunday | 0000001 | Seven text digits: 0=study day, 1=rest day. 0000011 means Monday-Friday.
Effort contingency | 20% | Extra effort applied once to each remaining task estimate.
Usable time fraction | 85% | Allows for interruptions; 85% of entered hours is scheduled.
Core allocation | 60% | Fraction of usable daily time reserved for core concepts and implementation.
Practice allocation | 20% | Fraction reserved for DSA, SQL, numerical ML, and revision.
Delivery allocation | 20% | Fraction reserved for discovery, capstone work, security, UAT, and handover.
Core hours per study day | 1.53 | Calculated; capacity is not duplicated between lanes.
Practice hours per study day | 0.51 | Calculated.
Delivery hours per study day | 0.51 | Calculated.
Study days per week | 6 | Count of zeroes in the weekend pattern.
Allocation total | 100% | Must equal 100%.
Input status | Ready | Invalid inputs suppress schedule dates rather than invent a finish date.

## Dashboard
Measure | Calculated Result | Interpretation | Overview
Plan status | Ready | A blocked or invalid plan does not display a misleading finish date.
Selected unbuffered hours | 900 | Original illustrative estimates for included modules; edit estimates after an initial diagnostic.
Remaining buffered hours | 1080 | Remaining estimate multiplied by contingency. Idle time from dependencies or lane reservations is not counted as study effort.
Effort-weighted completion | 0% | Estimate-weighted progress, not a guarantee of mastery.
Forecast finish | 2028-08-09 | Forecast for the selected remaining plan. This is not a job-readiness promise.
Remaining study-day span | 562 | Includes waiting caused by prerequisites and fixed lane allocations.
Calendar-day span | 656
Approximate study weeks | 93.6667 | Study-day span divided by study days per week; holidays can increase calendar time.
Core daily usable hours | 1.53
Practice daily usable hours | 0.51
Delivery daily usable hours | 0.51
Timeline display window | Within 104-week chart
Hours/day scenario | Estimated finish | Same scope, progress, allocation, calendar, and contingency; change those inputs in Settings.
1 | 2032-03-11
2 | 2029-07-03
3 | 2028-08-09
4 | 2028-02-28
6 | 2027-09-16
Formulas:
Calculated Result = IF(B2="Ready",WORKDAY.INTL(Settings!$B2-1,MAX(1,ROUNDUP(MAX(Schedule!$O2:O49)*Settings!$B3/[Measure],0)),Settings!$B4,Holidays!$A2:A101),"")

## Schedule
ID | Learning module | Lane | Include 1/0 | Estimate hours | Complete % | Prerequisite 1 | Prerequisite 2 | Prerequisite 3 | Prerequisite 4 | Remaining buffered hours | Lane hours/day | Status | Start study-day offset | Finish study-day offset | Planned start | Planned finish | Study-day duration | Completion evidence | Practice / reference URL | Overview
F01 | FDE role and delivery orientation | Core | 1 | 4 | 0% |  |  |  |  | 4.8 | 1.53 | Planned | 0 | 3.1373 | 2026-10-24 | 2026-10-28 | 3.1373 | Explain customer ownership, role boundaries, and a reason to stop an engagement. | https://roadmap.sh/forward-deployed-engineer
F02 | Primary language: Python | Core | 1 | 32 | 0% | F01 |  |  |  | 38.4 | 1.53 | Planned | 3.1373 | 28.2353 | 2026-10-28 | 2026-11-26 | 25.098 | Run a tested ingestion command in a fresh environment. | https://www.deep-ml.com/paths
F03 | Git Linux and debugging foundations | Core | 1 | 18 | 0% | F02 |  |  |  | 21.6 | 1.53 | Planned | 28.2353 | 42.3529 | 2026-11-26 | 2026-12-12 | 14.1176 | Diagnose a failed service and deliver a reviewable change. | https://roadmap.sh/git-github
F04 | Testing and reproducible project bridge | Core | 1 | 20 | 0% | F03 |  |  |  | 24 | 1.53 | Planned | 42.3529 | 58.0392 | 2026-12-12 | 2026-12-31 | 15.6863 | Write unit, integration, and contract tests with fixtures and a CI check. | https://abseil.io/resources/swe-book
F05 | HTTP backend and API contracts | Core | 1 | 30 | 0% | F04 |  |  |  | 36 | 1.53 | Planned | 58.0392 | 81.5686 | 2026-12-31 | 2027-01-27 | 23.5294 | Build a validated API and durable job workflow with explicit errors. | https://roadmap.sh/backend
F06 | SQL relational modeling and PostgreSQL | Core | 1 | 32 | 0% | F03 |  |  |  | 38.4 | 1.53 | Planned | 81.5686 | 106.6667 | 2027-01-27 | 2027-02-25 | 25.098 | Reconcile joins, constrain data, inspect a plan, and restore a test backup. | https://datalemur.com/
F07 | One usable frontend stack | Core | 1 | 32 | 0% | F05 |  |  |  | 38.4 | 1.53 | Planned | 106.6667 | 131.7647 | 2027-02-25 | 2027-03-26 | 25.098 | Complete an accessible review flow including failure and loading states. | https://roadmap.sh/frontend
F08 | Data lifecycle pipelines and quality | Core | 1 | 28 | 0% | F06 | F04 |  |  | 33.6 | 1.53 | Planned | 131.7647 | 153.7255 | 2027-03-26 | 2027-04-21 | 21.9608 | Trace a serving record to source and replay data without duplication. | https://roadmap.sh/data-engineer
B01 | Linear algebra and numerical reasoning bridge | Core | 1 | 18 | 0% | F02 |  |  |  | 21.6 | 1.53 | Planned | 153.7255 | 167.8431 | 2027-04-21 | 2027-05-07 | 14.1176 | Test matrix shapes, normalization, similarity, and zero-vector behavior. | https://www.deep-ml.com/paths
B02 | Probability statistics and uncertainty bridge | Core | 1 | 20 | 0% | B01 |  |  |  | 24 | 1.53 | Planned | 167.8431 | 183.5294 | 2027-05-07 | 2027-05-26 | 15.6863 | Explain base rates, sampling uncertainty, and a confidence interval. | https://www.deep-ml.com/paths
B03 | NumPy pandas and data manipulation bridge | Core | 1 | 18 | 0% | B01 | F06 |  |  | 21.6 | 1.53 | Planned | 183.5294 | 197.6471 | 2027-05-26 | 2027-06-11 | 14.1176 | Produce a reproducible audit with missing data and duplicate-key checks. | https://www.deep-ml.com/paths
B04 | Calculus gradients and optimization bridge | Core | 1 | 12 | 0% | B01 |  |  |  | 14.4 | 1.53 | Planned | 197.6471 | 207.0588 | 2027-06-11 | 2027-06-23 | 9.4118 | Implement and check one gradient update and learning-rate failure. | https://www.deep-ml.com/paths
B05 | Classical ML baselines and leakage bridge | Core | 1 | 26 | 0% | B02 | B03 | B04 |  | 31.2 | 1.53 | Planned | 207.0588 | 227.451 | 2027-06-23 | 2027-07-16 | 20.3922 | Compare regression or classification against a baseline using leakage-safe splits. | https://www.deep-ml.com/paths
B06 | Metrics thresholds and experimental reasoning bridge | Core | 1 | 20 | 0% | B05 |  |  |  | 24 | 1.53 | Planned | 227.451 | 243.1373 | 2027-07-16 | 2027-08-04 | 15.6863 | Choose task metrics and distinguish a score difference from a causal claim. | https://datalemur.com/
A01 | LLM behavior and model selection | Core | 1 | 20 | 0% | B05 |  |  |  | 24 | 1.53 | Planned | 243.1373 | 258.8235 | 2027-08-04 | 2027-08-21 | 15.6863 | Compare candidate approaches with quality, policy, latency, and cost evidence. | https://roadmap.sh/ai-engineer
A02 | Prompt context and prompt lifecycle | Core | 1 | 22 | 0% | A01 |  |  |  | 26.4 | 1.53 | Planned | 258.8235 | 276.0784 | 2027-08-21 | 2027-09-11 | 17.2549 | Version a schema-constrained prompt and a permission-filtered context packet. | https://roadmap.sh/prompt-engineering
A03 | Retrieval embeddings and vector stores | Core | 1 | 30 | 0% | A02 | F08 |  |  | 36 | 1.53 | Planned | 276.0784 | 299.6078 | 2027-09-11 | 2027-10-08 | 23.5294 | Measure retrieval separately and verify citation support and tenant isolation. | https://roadmap.sh/ai-engineer
A04 | Evaluation pipelines and regression analysis | Core | 1 | 26 | 0% | A03 | B06 |  |  | 31.2 | 1.53 | Planned | 299.6078 | 320 | 2027-10-08 | 2027-11-01 | 20.3922 | Produce a versioned held-out report with errors separate from poor scores. | https://eugeneyan.com/writing/
S01 | Authentication API and system security | Core | 1 | 24 | 0% | F05 |  |  |  | 28.8 | 1.53 | Planned | 320 | 338.8235 | 2027-11-02 | 2027-11-23 | 18.8235 | Reject invalid credentials, cross-tenant access, and unsafe output use. | https://genai.owasp.org/llm-top-10/
A05 | Trusted tools state and integration | Core | 1 | 26 | 0% | A04 | S01 |  |  | 31.2 | 1.53 | Planned | 338.8235 | 359.2157 | 2027-11-23 | 2027-12-17 | 20.3922 | Reject malformed or unauthorized tool calls and recover a partial integration failure. | https://roadmap.sh/ai-agents
A06 | Bounded agents and architecture tradeoffs | Core | 1 | 24 | 0% | A05 |  |  |  | 28.8 | 1.53 | Planned | 359.2157 | 378.0392 | 2027-12-17 | 2028-01-08 | 18.8235 | Compare a fixed workflow and agent with budgets, stopping rules, and task evaluations. | https://roadmap.sh/ai-agents
A07 | AI-assisted development discipline | Core | 1 | 8 | 0% | F04 |  |  |  | 9.6 | 1.53 | Planned | 378.0392 | 384.3137 | 2028-01-08 | 2028-01-15 | 6.2745 | Explain generated code changes and independently validate acceptance behavior. | https://roadmap.sh/vibe-coding
C01 | One cloud and container deployment | Core | 1 | 26 | 0% | S01 |  |  |  | 31.2 | 1.53 | Planned | 384.3137 | 404.7059 | 2028-01-15 | 2028-02-08 | 20.3922 | Deploy a sandbox service with scoped identity, private data, and a budget. | https://roadmap.sh/aws
C02 | Infrastructure as code and release workflow | Core | 1 | 24 | 0% | C01 |  |  |  | 28.8 | 1.53 | Planned | 404.7059 | 423.5294 | 2028-02-08 | 2028-03-01 | 18.8235 | Review infrastructure changes and rehearse a controlled rollout and recovery. | https://roadmap.sh/terraform
C03 | Observability and inference measurement | Core | 1 | 24 | 0% | A04 | C02 |  |  | 28.8 | 1.53 | Planned | 423.5294 | 442.3529 | 2028-03-01 | 2028-03-23 | 18.8235 | Find a failed stage in a redacted trace and measure quality-preserving optimization. | https://opentelemetry.io/docs/
C04 | Model and application release lifecycle | Core | 1 | 14 | 0% | C03 |  |  |  | 16.8 | 1.53 | Planned | 442.3529 | 453.3333 | 2028-03-23 | 2028-04-05 | 10.9804 | Pin model, prompt, dataset, evaluator, index, and application artifacts. | https://madewithml.com/
P01 | DSA fundamentals and first pattern exercises | Practice | 1 | 22 | 0% | F02 |  |  |  | 26.4 | 0.51 | Planned | 28.2353 | 80 | 2026-11-26 | 2027-01-25 | 51.7647 | Implement basic structures and explain correctness and complexity. | https://neetcode.io/roadmap
P02 | SQL practice with duplicates NULL and windows | Practice | 1 | 26 | 0% | F06 |  |  |  | 31.2 | 0.51 | Planned | 106.6667 | 167.8431 | 2027-02-25 | 2027-05-07 | 61.1765 | Solve representative SQL cases and state output grain and edge behavior. | https://datalemur.com/questions
P03 | DSA pattern practice and spaced review | Practice | 1 | 44 | 0% | P01 |  |  |  | 52.8 | 0.51 | Planned | 167.8431 | 271.3725 | 2027-05-07 | 2027-09-06 | 103.5294 | Solve unseen variants across trees, heaps, graphs, and introductory dynamic programming. | https://leetcode.com/problemset/
P04 | ML and mathematical coding practice | Practice | 1 | 26 | 0% | B05 |  |  |  | 31.2 | 0.51 | Planned | 271.3725 | 332.549 | 2027-09-06 | 2027-11-16 | 61.1765 | Implement selected Deep-ML problems and explain numerical and model behavior. | https://www.deep-ml.com/paths
P05 | Timed DSA and system-design explanation | Practice | 1 | 22 | 0% | P03 | F05 |  |  | 26.4 | 0.51 | Planned | 332.549 | 384.3137 | 2027-11-16 | 2028-01-15 | 51.7647 | Complete a mock coding or design exercise with explicit tradeoffs and edge tests. | https://neetcode.io/practice
P06 | Mixed SQL ML DSA revision and interview evidence | Practice | 1 | 20 | 0% | P02 | P04 | P05 |  | 24 | 0.51 | Planned | 384.3137 | 431.3725 | 2028-01-15 | 2028-03-10 | 47.0588 | Revisit mistakes unaided and present a measured project case study. | https://datalemur.com/
D01 | Discovery and business workflow framing | Delivery | 1 | 10 | 0% | F01 |  |  |  | 12 | 0.51 | Planned | 3.1373 | 26.6667 | 2026-10-28 | 2026-11-24 | 23.5294 | Write a pilot brief with users, baseline, constraints, assumptions, and stop criteria. | https://www.momtestbook.com/
D02 | Requirements scoping and stakeholder alignment | Delivery | 1 | 12 | 0% | D01 |  |  |  | 14.4 | 0.51 | Planned | 26.6667 | 54.902 | 2026-11-24 | 2026-12-26 | 28.2353 | Agree acceptance evidence and decision ownership with representative stakeholders. | https://roadmap.sh/forward-deployed-engineer
D03 | Privacy governance and data permissions | Delivery | 1 | 12 | 0% | D02 |  |  |  | 14.4 | 0.51 | Planned | 54.902 | 83.1373 | 2026-12-26 | 2027-01-29 | 28.2353 | Document data flows, retention, permissions, vendor assumptions, and review owners. | https://www.nist.gov/itl/ai-risk-management-framework
D04 | Capstone data audit and non-AI baseline | Delivery | 1 | 14 | 0% | F08 | D03 |  |  | 16.8 | 0.51 | Planned | 153.7255 | 186.6667 | 2027-04-21 | 2027-05-29 | 32.9412 | Build a synthetic multi-tenant dataset and reconcile baseline task measurements. | https://datalemur.com/
D05 | Capstone full-stack vertical slice | Delivery | 1 | 28 | 0% | F07 | D04 |  |  | 33.6 | 0.51 | Planned | 186.6667 | 252.549 | 2027-05-29 | 2027-08-14 | 65.8824 | Deliver an authenticated operator flow with durable state and explicit errors. | https://roadmap.sh/full-stack
D06 | Capstone retrieval and evaluation pilot | Delivery | 1 | 24 | 0% | A04 | D05 |  |  | 28.8 | 0.51 | Planned | 320 | 376.4706 | 2027-11-02 | 2028-01-06 | 56.4706 | Demonstrate supported answers, abstention, and versioned case-level evaluations. | https://eugeneyan.com/writing/
D07 | Capstone bounded actions and failure rehearsal | Delivery | 1 | 16 | 0% | A06 | D06 | D03 |  | 19.2 | 0.51 | Planned | 378.0392 | 415.6863 | 2028-01-08 | 2028-02-21 | 37.6471 | Demonstrate trusted approval, replay-safe actions, and recovery from a tool outage. | https://genai.owasp.org/llm-top-10/
D08 | Deployment user acceptance and recovery | Delivery | 1 | 20 | 0% | C04 | D07 |  |  | 24 | 0.51 | Planned | 453.3333 | 500.3922 | 2028-04-05 | 2028-05-30 | 47.0588 | Run representative UAT and rehearse deployment, restore, and rollback or roll-forward. | https://sre.google/books/
D09 | Operational handover and technical writing | Delivery | 1 | 14 | 0% | D08 |  |  |  | 16.8 | 0.51 | Planned | 500.3922 | 533.3333 | 2028-05-30 | 2028-07-07 | 32.9412 | Another engineer can operate, diagnose, and recover using the runbook. | https://abseil.io/resources/swe-book
D10 | Value report feedback and portfolio | Delivery | 1 | 12 | 0% | D09 |  |  |  | 14.4 | 0.51 | Planned | 533.3333 | 561.5686 | 2028-07-07 | 2028-08-09 | 28.2353 | Present measured value, uncertainty, adoption, cost, product feedback, and next decisions. | https://www.momtestbook.com/
O01 | Optional additional programming languages | Core | 0 | 24 | 0% | F03 |  |  |  | 0 | 1.53 | Skipped | 453.3333 | 453.3333 |  |  | 0 | Choose only the language needed by the target role and demonstrate one integration. | https://roadmap.sh/
O02 | Optional alternative cloud depth | Core | 0 | 18 | 0% | C01 |  |  |  | 0 | 1.53 | Skipped | 453.3333 | 453.3333 |  |  | 0 | Choose a justified additional cloud or replace AWS in the baseline plan. | https://roadmap.sh/devops
O03 | Optional distributed processing and orchestration | Core | 0 | 22 | 0% | F08 |  |  |  | 0 | 1.53 | Skipped | 453.3333 | 453.3333 |  |  | 0 | Demonstrate an idempotent backfill or justified distributed job. | https://roadmap.sh/data-engineer
O04 | Optional Kubernetes operations | Core | 0 | 18 | 0% | C01 |  |  |  | 0 | 1.53 | Skipped | 453.3333 | 453.3333 |  |  | 0 | Diagnose a failed rollout with appropriate resource, network, and access controls. | https://roadmap.sh/kubernetes
O05 | Optional alternative stores APIs and runtimes | Core | 0 | 18 | 0% | F05 |  |  |  | 0 | 1.53 | Skipped | 453.3333 | 453.3333 |  |  | 0 | Choose only a needed alternative and defend its access patterns and operational tradeoffs. | https://roadmap.sh/backend
O06 | Optional coding-agent product comparison | Core | 0 | 8 | 0% | A07 |  |  |  | 0 | 1.53 | Skipped | 453.3333 | 453.3333 |  |  | 0 | Pilot one or two tools in a sandbox with explicit permission and privacy checks. | https://roadmap.sh/vibe-coding
Formulas:
Planned start = IF(AND([Status]="Planned",[Remaining buffered hours]>0),WORKDAY.INTL(Settings!$B2-1,INT([Start study-day offset]+0.000000001)+1,Settings!$B4,Holidays!$A2:A101),"")
Planned finish = IF(AND([Status]="Planned",[Remaining buffered hours]>0),WORKDAY.INTL(Settings!$B2-1,MAX(1,ROUNDUP([Finish study-day offset]-0.000000001,0)),Settings!$B4,Holidays!$A2:A101),"")

## Weekly Timeline
Module | Lane | Start | Finish | 2026-10-24 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-28 | 2026-12-05 | 2026-12-12 | 2026-12-19 | 2026-12-26 | 2027-01-02 | 2027-01-09 | 2027-01-16 | 2027-01-23 | 2027-01-30 | 2027-02-06 | 2027-02-13 | 2027-02-20 | 2027-02-27 | 2027-03-06 | 2027-03-13 | 2027-03-20 | 2027-03-27 | 2027-04-03 | 2027-04-10 | 2027-04-17 | 2027-04-24 | 2027-05-01 | 2027-05-08 | 2027-05-15 | 2027-05-22 | 2027-05-29 | 2027-06-05 | 2027-06-12 | 2027-06-19 | 2027-06-26 | 2027-07-03 | 2027-07-10 | 2027-07-17 | 2027-07-24 | 2027-07-31 | 2027-08-07 | 2027-08-14 | 2027-08-21 | 2027-08-28 | 2027-09-04 | 2027-09-11 | 2027-09-18 | 2027-09-25 | 2027-10-02 | 2027-10-09 | 2027-10-16 | 2027-10-23 | 2027-10-30 | 2027-11-06 | 2027-11-13 | 2027-11-20 | 2027-11-27 | 2027-12-04 | 2027-12-11 | 2027-12-18 | 2027-12-25 | 2028-01-01 | 2028-01-08 | 2028-01-15 | 2028-01-22 | 2028-01-29 | 2028-02-05 | 2028-02-12 | 2028-02-19 | 2028-02-26 | 2028-03-04 | 2028-03-11 | 2028-03-18 | 2028-03-25 | 2028-04-01 | 2028-04-08 | 2028-04-15 | 2028-04-22 | 2028-04-29 | 2028-05-06 | 2028-05-13 | 2028-05-20 | 2028-05-27 | 2028-06-03 | 2028-06-10 | 2028-06-17 | 2028-06-24 | 2028-07-01 | 2028-07-08 | 2028-07-15 | 2028-07-22 | 2028-07-29 | 2028-08-05 | 2028-08-12 | 2028-08-19 | 2028-08-26 | 2028-09-02 | 2028-09-09 | 2028-09-16 | 2028-09-23 | 2028-09-30 | 2028-10-07 | 2028-10-14 | Overview
FDE role and delivery orientation | Core | 2026-10-24 | 2026-10-28 | 1
Primary language: Python | Core | 2026-10-28 | 2026-11-26 | 1 | 1 | 1 | 1 | 1
Git Linux and debugging foundations | Core | 2026-11-26 | 2026-12-12 |  |  |  |  | 1 | 1 | 1 | 1
Testing and reproducible project bridge | Core | 2026-12-12 | 2026-12-31 | [7 empty] | 1 | 1 | 1
HTTP backend and API contracts | Core | 2026-12-31 | 2027-01-27 | [9 empty] | 1 | 1 | 1 | 1 | 1
SQL relational modeling and PostgreSQL | Core | 2027-01-27 | 2027-02-25 | [13 empty] | 1 | 1 | 1 | 1 | 1
One usable frontend stack | Core | 2027-02-25 | 2027-03-26 | [17 empty] | 1 | 1 | 1 | 1 | 1
Data lifecycle pipelines and quality | Core | 2027-03-26 | 2027-04-21 | [21 empty] | 1 | 1 | 1 | 1 | 1
Linear algebra and numerical reasoning bridge | Core | 2027-04-21 | 2027-05-07 | [25 empty] | 1 | 1 | 1
Probability statistics and uncertainty bridge | Core | 2027-05-07 | 2027-05-26 | [27 empty] | 1 | 1 | 1 | 1
NumPy pandas and data manipulation bridge | Core | 2027-05-26 | 2027-06-11 | [30 empty] | 1 | 1 | 1
Calculus gradients and optimization bridge | Core | 2027-06-11 | 2027-06-23 | [32 empty] | 1 | 1 | 1
Classical ML baselines and leakage bridge | Core | 2027-06-23 | 2027-07-16 | [34 empty] | 1 | 1 | 1 | 1
Metrics thresholds and experimental reasoning bridge | Core | 2027-07-16 | 2027-08-04 | [37 empty] | 1 | 1 | 1 | 1
LLM behavior and model selection | Core | 2027-08-04 | 2027-08-21 | [40 empty] | 1 | 1 | 1 | 1
Prompt context and prompt lifecycle | Core | 2027-08-21 | 2027-09-11 | [43 empty] | 1 | 1 | 1 | 1
Retrieval embeddings and vector stores | Core | 2027-09-11 | 2027-10-08 | [46 empty] | 1 | 1 | 1 | 1
Evaluation pipelines and regression analysis | Core | 2027-10-08 | 2027-11-01 | [49 empty] | 1 | 1 | 1 | 1 | 1
Authentication API and system security | Core | 2027-11-02 | 2027-11-23 | [53 empty] | 1 | 1 | 1 | 1
Trusted tools state and integration | Core | 2027-11-23 | 2027-12-17 | [56 empty] | 1 | 1 | 1 | 1
Bounded agents and architecture tradeoffs | Core | 2027-12-17 | 2028-01-08 | [59 empty] | 1 | 1 | 1 | 1 | 1
AI-assisted development discipline | Core | 2028-01-08 | 2028-01-15 | [63 empty] | 1 | 1
One cloud and container deployment | Core | 2028-01-15 | 2028-02-08 | [64 empty] | 1 | 1 | 1 | 1
Infrastructure as code and release workflow | Core | 2028-02-08 | 2028-03-01 | [67 empty] | 1 | 1 | 1 | 1
Observability and inference measurement | Core | 2028-03-01 | 2028-03-23 | [70 empty] | 1 | 1 | 1 | 1
Model and application release lifecycle | Core | 2028-03-23 | 2028-04-05 | [73 empty] | 1 | 1 | 1
DSA fundamentals and first pattern exercises | Practice | 2026-11-26 | 2027-01-25 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
SQL practice with duplicates NULL and windows | Practice | 2027-02-25 | 2027-05-07 | [17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
DSA pattern practice and spaced review | Practice | 2027-05-07 | 2027-09-06 | [27 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
ML and mathematical coding practice | Practice | 2027-09-06 | 2027-11-16 | [45 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Timed DSA and system-design explanation | Practice | 2027-11-16 | 2028-01-15 | [55 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Mixed SQL ML DSA revision and interview evidence | Practice | 2028-01-15 | 2028-03-10 | [64 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Discovery and business workflow framing | Delivery | 2026-10-28 | 2026-11-24 | 1 | 1 | 1 | 1 | 1
Requirements scoping and stakeholder alignment | Delivery | 2026-11-24 | 2026-12-26 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
Privacy governance and data permissions | Delivery | 2026-12-26 | 2027-01-29 | [9 empty] | 1 | 1 | 1 | 1 | 1
Capstone data audit and non-AI baseline | Delivery | 2027-04-21 | 2027-05-29 | [25 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Capstone full-stack vertical slice | Delivery | 2027-05-29 | 2027-08-14 | [31 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Capstone retrieval and evaluation pilot | Delivery | 2027-11-02 | 2028-01-06 | [53 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Capstone bounded actions and failure rehearsal | Delivery | 2028-01-08 | 2028-02-21 | [63 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
Deployment user acceptance and recovery | Delivery | 2028-04-05 | 2028-05-30 | [75 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Operational handover and technical writing | Delivery | 2028-05-30 | 2028-07-07 | [83 empty] | 1 | 1 | 1 | 1 | 1 | 1
Value report feedback and portfolio | Delivery | 2028-07-07 | 2028-08-09 | [88 empty] | 1 | 1 | 1 | 1 | 1 | 1
Optional additional programming languages | Core
Optional alternative cloud depth | Core
Optional distributed processing and orchestration | Core
Optional Kubernetes operations | Core
Optional alternative stores APIs and runtimes | Core
Optional coding-agent product comparison | Core

## Topic Map
Original Topic | Track | Scheduled Module | Module Name | Include 1/0 | Status | Concept-to-practice evidence | Overview
Introduction | 01 Role and Glossary | F01 | FDE role and delivery orientation | 1 | Planned | Explain the engagement from business pain to operating ownership, including a reason to stop the project.
Roles & Responsabilities | 01 Role and Glossary | F01 | FDE role and delivery orientation | 1 | Planned | Every delivery activity has an accountable owner and an explicit handoff condition.
From X to FDE | 01 Role and Glossary | F01 | FDE role and delivery orientation | 1 | Planned | A portfolio includes a working system, decision log, measured result, and honest failure analysis.
FDE Tiers | 01 Role and Glossary | F01 | FDE role and delivery orientation | 1 | Planned | Explain which roles fit your evidence today and the concrete gaps for the next scope of ownership.
Delta | 01 Role and Glossary | F01 | FDE role and delivery orientation | 1 | Planned | Resolve the meaning from context and avoid treating one company's terminology as an industry standard.
Last-Mile Integration | 01 Role and Glossary | A05 | Trusted tools state and integration | 1 | Planned | A user completes the real task in the target workflow, including error and fallback paths.
Day 2 Operations | 01 Role and Glossary | D09 | Operational handover and technical writing | 1 | Planned | Another engineer can detect, diagnose, recover, and communicate an incident using the runbook.
UAT | 01 Role and Glossary | D08 | Deployment user acceptance and recovery | 1 | Planned | Business owners sign off on documented workflows, limitations, unresolved defects, and release conditions.
Productized Consulting | 01 Role and Glossary | F01 | FDE role and delivery orientation | 1 | Planned | An engagement can be repeated with consistent artifacts while exceptions remain explicit.
Embedded Engineering | 01 Role and Glossary | F01 | FDE role and delivery orientation | 1 | Planned | The customer can operate the delivered workflow and the product team receives reusable requirements.
Learn a Language | 02 Programming and Systems | F02 | Primary language: Python | 1 | Planned | Implement and troubleshoot an end-to-end feature without relying on generated code you cannot explain.
Python | 02 Programming and Systems | F02 | Primary language: Python | 1 | Planned | A fresh environment can run documented commands, tests, and a sample job with deterministic fixture inputs.
JavaScript / TypeScript | 02 Programming and Systems | F07 | One usable frontend stack | 1 | Planned | Malformed responses fail visibly and safely while valid responses retain useful inferred types.
Java / Scala | 02 Programming and Systems | O01 | Optional additional programming languages | 0 | Skipped | Explain the build, runtime configuration, failure handling, and integration contract of the changed component.
Go | 02 Programming and Systems | O01 | Optional additional programming languages | 0 | Skipped | The tool stays within its concurrency budget and terminates predictably under timeouts.
Rust | 02 Programming and Systems | O01 | Optional additional programming languages | 0 | Skipped | Justify the language choice and show correct error handling without unexplained unsafe operations.
C++ | 02 Programming and Systems | O01 | Optional additional programming languages | 0 | Skipped | Explain the ownership model and validate the relevant boundary with a focused test or sanitizer run.
DSA & System Design | 02 Programming and Systems | P01 | DSA fundamentals and first pattern exercises | 1 | Planned | Defend a simple design numerically and identify the first bottleneck and recovery path.
Git & GitHub | 02 Programming and Systems | F03 | Git Linux and debugging foundations | 1 | Planned | Another engineer can review, reproduce, and safely revert the feature.
Linux Skills | 02 Programming and Systems | F03 | Git Linux and debugging foundations | 1 | Planned | Produce a minimal diagnosis with evidence and recover without weakening access controls.
Frontend Skills | 03 Full Stack and Data | F07 | One usable frontend stack | 1 | Planned | Users can complete the task with keyboard navigation and clear feedback on network or permission failures.
HTML | 03 Full Stack and Data | F07 | One usable frontend stack | 1 | Planned | The interface remains understandable without styling and usable with keyboard-only navigation.
CSS | 03 Full Stack and Data | F07 | One usable frontend stack | 1 | Planned | No important content overlaps or becomes inaccessible at supported viewport sizes and zoom levels.
JavaScript | 03 Full Stack and Data | F07 | One usable frontend stack | 1 | Planned | Out-of-order responses, retries, and user cancellation behave predictably in a small test.
React | 03 Full Stack and Data | F07 | One usable frontend stack | 1 | Planned | Component behavior is explainable under rerenders, request failures, and navigation.
Backend Skills | 03 Full Stack and Data | F05 | HTTP backend and API contracts | 1 | Planned | A duplicate request or failed worker cannot silently corrupt state or cross tenant boundaries.
Node.js | 03 Full Stack and Data | O05 | Optional alternative stores APIs and runtimes | 0 | Skipped | Concurrent requests remain responsive while large or malformed uploads are rejected safely.
SQL | 03 Full Stack and Data | F06 | SQL relational modeling and PostgreSQL | 1 | Planned | Reconcile query output with a hand-checked sample and explain the query plan for realistic data volume.
PostgreSQL | 03 Full Stack and Data | F06 | SQL relational modeling and PostgreSQL | 1 | Planned | Demonstrate concurrency correctness, query performance, and a documented restore procedure.
NoSQL DBs | 03 Full Stack and Data | O05 | Optional alternative stores APIs and runtimes | 0 | Skipped | Explain exactly which queries and consistency guarantees justify the chosen store.
APIs Design | 03 Full Stack and Data | F05 | HTTP backend and API contracts | 1 | Planned | Clients can distinguish accepted work, completed work, retryable failure, and permanent rejection.
GraphQL | 03 Full Stack and Data | O05 | Optional alternative stores APIs and runtimes | 0 | Skipped | A nested query has bounded cost and the same authorization guarantees as direct API access.
Data Engineering Skills | 03 Full Stack and Data | F08 | Data lifecycle pipelines and quality | 1 | Planned | A sampled output can be traced to its source and regenerated after a controlled backfill.
Data Modeling | 03 Full Stack and Data | F06 | SQL relational modeling and PostgreSQL | 1 | Planned | Two engineers derive the same metric and authorization result from the documented model.
Data Pipelines | 03 Full Stack and Data | F08 | Data lifecycle pipelines and quality | 1 | Planned | A restart or replay produces the documented result without unexplained loss or duplication.
Data Warehouses | 03 Full Stack and Data | F08 | Data lifecycle pipelines and quality | 1 | Planned | A business metric reconciles with source samples and its refresh delay and caveats are visible.
Spark | 03 Full Stack and Data | O03 | Optional distributed processing and orchestration | 0 | Skipped | Explain the execution plan, data movement, and cost of a representative job.
Airflow | 03 Full Stack and Data | O03 | Optional distributed processing and orchestration | 0 | Skipped | A failed task can be retried and a past interval can be reproduced with documented inputs.
AI Engineering Skills | 04 AI Engineering | A01 | LLM behavior and model selection | 1 | Planned | A repeatable evaluation shows improvement over a simple baseline within an agreed operational budget.
LLM Fundamentals | 04 AI Engineering | A01 | LLM behavior and model selection | 1 | Planned | Explain why a response was accepted or rejected using evidence, validation, and the provider's actual data policy.
Prompt Engineering | 04 AI Engineering | A02 | Prompt context and prompt lifecycle | 1 | Planned | A prompt revision improves measured outcomes without breaking existing cases or weakening boundaries.
Context Engineering | 04 AI Engineering | A02 | Prompt context and prompt lifecycle | 1 | Planned | Explain why every included item is relevant, authorized, current enough, and worth its token cost.
RAGs | 04 AI Engineering | A03 | Retrieval embeddings and vector stores | 1 | Planned | Answers cite passages that support their claims, and unauthorized documents never enter the model context.
Vector DBs | 04 AI Engineering | A03 | Retrieval embeddings and vector stores | 1 | Planned | Measure recall, latency, freshness, deletion behavior, and tenant isolation under representative queries.
Choosing Model Providers | 04 AI Engineering | A01 | LLM behavior and model selection | 1 | Planned | A decision record contains measured task results, policy checks, a cost model, and a tested fallback policy.
Prompt Management | 04 AI Engineering | A02 | Prompt context and prompt lifecycle | 1 | Planned | Reproduce which prompt, model, retrieval configuration, and tool schema generated a given output.
AI Agents | 05 Agents and Coding Tools | A06 | Bounded agents and architecture tradeoffs | 1 | Planned | The agent stops safely, reports uncertainty, and cannot perform an action outside server-enforced authority.
Agent Architectures | 05 Agents and Coding Tools | A06 | Bounded agents and architecture tradeoffs | 1 | Planned | Choose the simplest architecture that meets the measured requirements and explain why alternatives lose.
Tools & Functions | 05 Agents and Coding Tools | A05 | Trusted tools state and integration | 1 | Planned | Malformed, unauthorized, repeated, and excessive calls are rejected before any side effect.
Memory & State | 05 Agents and Coding Tools | A05 | Trusted tools state and integration | 1 | Planned | A restart resumes predictably, sensitive memory can be deleted, and side effects are not duplicated.
MCP | 05 Agents and Coding Tools | A05 | Trusted tools state and integration | 1 | Planned | A client discovers capabilities and uses only authorized operations with bounded, auditable behavior.
Multi-Agents | 05 Agents and Coding Tools | A06 | Bounded agents and architecture tradeoffs | 1 | Planned | A measured improvement justifies coordination cost and responsibility for final decisions remains explicit.
Vibe Coding | 05 Agents and Coding Tools | A07 | AI-assisted development discipline | 1 | Planned | The generated feature meets a written acceptance criterion and passes the same review gates as human-written code.
Claude Code | 05 Agents and Coding Tools | O06 | Optional coding-agent product comparison | 0 | Skipped | You can reconstruct the task, permissions, changes, validation, and remaining risk from the session evidence.
Codex | 05 Agents and Coding Tools | O06 | Optional coding-agent product comparison | 0 | Skipped | The chosen mode has documented permissions, reproducible output, and independently checked changes.
Gemini | 05 Agents and Coding Tools | O06 | Optional coding-agent product comparison | 0 | Skipped | Document the exact endpoint, model, account policy, limits, cost, and measured task results.
Cursor | 05 Agents and Coding Tools | O06 | Optional coding-agent product comparison | 0 | Skipped | The feature is verified and the organization's rules for indexed or transmitted code are respected.
OpenClaw | 05 Agents and Coding Tools | O06 | Optional coding-agent product comparison | 0 | Skipped | A documented threat model and bounded pilot justify every permission and provide a clear kill switch.
OpenCode | 05 Agents and Coding Tools | O06 | Optional coding-agent product comparison | 0 | Skipped | Document which code and prompts leave the machine and which commands the tool can execute.
Integration Engineering | 06 Integration Cloud and DevOps | A05 | Trusted tools state and integration | 1 | Planned | After an induced failure, both systems reconcile to the documented business state.
Working with Legacy Systems | 06 Integration Cloud and DevOps | A05 | Trusted tools state and integration | 1 | Planned | A parallel run demonstrates equivalence or documented improvements with a reversible rollout.
Cloud Platforms | 06 Integration Cloud and DevOps | C01 | One cloud and container deployment | 1 | Planned | Explain every trust boundary, recurring cost, and expected failure response in the deployment.
AWS | 06 Integration Cloud and DevOps | C01 | One cloud and container deployment | 1 | Planned | The workload can access only the required resources, and cost and recovery controls are demonstrated.
GCP | 06 Integration Cloud and DevOps | O02 | Optional alternative cloud depth | 0 | Skipped | Permissions, regional assumptions, telemetry, and monthly cost estimates are explicit and testable.
Azure | 06 Integration Cloud and DevOps | O02 | Optional alternative cloud depth | 0 | Skipped | A user and workload each receive only their required permissions and access revocation is tested.
Terraform | 06 Integration Cloud and DevOps | C02 | Infrastructure as code and release workflow | 1 | Planned | A second engineer can explain the plan, state storage, permissions, and destructive-change guardrails.
Containers | 06 Integration Cloud and DevOps | C01 | One cloud and container deployment | 1 | Planned | A fresh host runs the same image with explicit configuration, bounded resources, and no embedded secrets.
Docker | 06 Integration Cloud and DevOps | C01 | One cloud and container deployment | 1 | Planned | The published image is traceable to source and passes a documented runtime and dependency check.
Kubernetes | 06 Integration Cloud and DevOps | O04 | Optional Kubernetes operations | 0 | Skipped | You can diagnose a failed rollout and demonstrate least-privilege access and predictable recovery.
DevOps Skills | 06 Integration Cloud and DevOps | C02 | Infrastructure as code and release workflow | 1 | Planned | A release is reproducible and an unsuccessful change has a rehearsed rollback or roll-forward procedure.
Observability | 07 Production AI and Security | C03 | Observability and inference measurement | 1 | Planned | Given a failed task, identify the relevant stage and version without exposing unnecessary sensitive data.
Building Eval Pipelines | 07 Production AI and Security | A04 | Evaluation pipelines and regression analysis | 1 | Planned | A regression is detected reproducibly and the score can be traced to individual cases and explicit criteria.
Debugging Agent Logic | 07 Production AI and Security | A06 | Bounded agents and architecture tradeoffs | 1 | Planned | A minimal replay explains the failure and a focused test prevents its recurrence.
Inference Optimization | 07 Production AI and Security | C03 | Observability and inference measurement | 1 | Planned | An improvement is quantified at realistic concurrency and stays within the agreed quality and memory budget.
MLOps | 07 Production AI and Security | C04 | Model and application release lifecycle | 1 | Planned | A production result can be reproduced or explained from its artifact manifest and trace.
Security | 07 Production AI and Security | S01 | Authentication API and system security | 1 | Planned | Sensitive access and side effects remain blocked even when the model follows an adversarial instruction.
DevSecOps | 07 Production AI and Security | S01 | Authentication API and system security | 1 | Planned | A release has traceable artifacts, explicit risk decisions, and tested credential boundaries.
API Security | 07 Production AI and Security | S01 | Authentication API and system security | 1 | Planned | Negative authorization tests cover every sensitive read and write boundary.
Authentication | 07 Production AI and Security | S01 | Authentication API and system security | 1 | Planned | Invalid credentials fail safely and valid identities still require explicit object-level permissions.
AI Governance | 07 Production AI and Security | D03 | Privacy governance and data permissions | 1 | Planned | A reviewer can identify who approves changes, which evidence is required, and what triggers suspension.
Data Privacy & Compliance | 07 Production AI and Security | D03 | Privacy governance and data permissions | 1 | Planned | A data-flow record explains lawful handling decisions and demonstrates approved retention and deletion behavior.
Discovery & Scoping | 08 Customer Delivery | D01 | Discovery and business workflow framing | 1 | Planned | Stakeholders agree on the problem, decision owner, pilot boundary, and evidence needed to continue.
Requirements Gathering | 08 Customer Delivery | D02 | Requirements scoping and stakeholder alignment | 1 | Planned | Each critical requirement maps to a demonstration, measurement, test, or documented review.
Scoping & Sequencing | 08 Customer Delivery | D02 | Requirements scoping and stakeholder alignment | 1 | Planned | The first milestone tests a real project-killing assumption and later work depends on explicit evidence.
Scope, Speed, Quality | 08 Customer Delivery | D02 | Requirements scoping and stakeholder alignment | 1 | Planned | A written tradeoff names what is deferred, what remains mandatory, and who accepts the residual risk.
Communication | 08 Customer Delivery | D09 | Operational handover and technical writing | 1 | Planned | Each audience can state the current outcome, key risk, next action, and responsible owner.
Technical Writing | 08 Customer Delivery | D09 | Operational handover and technical writing | 1 | Planned | A new engineer can deploy, test, diagnose, and recover the supported workflow from the documentation.
Executive Reporting | 08 Customer Delivery | D10 | Value report feedback and portfolio | 1 | Planned | A sponsor can decide whether to continue, change scope, or stop based on the report.
Business Acumen | 09 Business and Product | D01 | Discovery and business workflow framing | 1 | Planned | Explain who benefits, who pays, what changes operationally, and what evidence would invalidate the business case.
Enterprise Workflow | 09 Business and Product | D01 | Discovery and business workflow framing | 1 | Planned | Every state transition, decision authority, and recovery path has a clear owner.
ROI & AI Impact | 09 Business and Product | D10 | Value report feedback and portfolio | 1 | Planned | The business case states assumptions, uncertainty, measured inputs, and the threshold for a worthwhile deployment.
Stakeholder Management | 09 Business and Product | D02 | Requirements scoping and stakeholder alignment | 1 | Planned | The right people approve the right decisions and unresolved disagreement is visible before release.
Product Feedback Loop | 09 Business and Product | D10 | Value report feedback and portfolio | 1 | Planned | A product decision is linked to customer evidence and the shipped change is checked against the original problem.
Time-to-Value | 09 Business and Product | D10 | Value report feedback and portfolio | 1 | Planned | The start, value event, cohort, exclusions, and sustained adoption check are explicit.

## Holidays
Holiday / excluded date | Reason | Overview

## Practice Log
Date | Platform | Topic / pattern | Problem URL or ID | Minutes | Outcome | Hint used? | Next review | Mistake / explanation / next action | Overview